## Sheet1
Tasks | Week 1 | Week 2 | Week 3 | Week 4
Authenticate with FB, Twitter, IG APIs | 5 | 3 | 2 | 2 | Numbers indicate estimated hours left to complete the task at the end of each week
Write code to make API calls to get user posts from platforms | 10 | 10 | 4 | 2
Start working on user interface | 4 | 2 | 6 | 4
Sketch out a more advanced user interface | 6 | 3 | 2 | 2
Enable sign up functionality for new users | 6 | 4 | 2 | 2
Enable sign in functionality for users | 6 | 4 | 2 | 2
Create backend database | 8 | 4 | 3 | 2