## Sheet1
Tasks | Week 1 | Week 2 | Week 3 | Week 4 | Notes
Make the timeline UI be an infinitely scrolling ListView | 15 | 10 | 3 | 1 |  | Numbers indicate estimated hours left to complete the task at the end of each week
Add functionality to get all posts "on this day" in the past | 10 | 7 | 7 | 5 | This will need to be implemented after we have the ability to store a user's entire timeline in Firebase
Add functionality to search for other Kronogram users by username | 10 | 10 | 10 | 8
Determine how to store a user's entire timeline in Firebase | 15 | 12 | 10 | 2
Determine how to display different types of posts | 20 | 17 | 15 | 3
Connect Kasey's UI components to existing functionality | 5 | 2 | 2 | 1
Redesign app bar for search feature | 10 | 5 | 2 | 2
Adjust timestamps based on user-specified timezone | 5 | 3 | 2 | 2