## Sheet1
Tasks | Week 1 | Week 2 | Week 3 | Notes
Add functionality to get all posts "on this day" in the past | 10 | 3 | 3 |  | Numbers indicate estimated hours left to complete the task at the end of each week
Set up relationship network between users | 20 | 15 | 10
Create view to see other users' timelines from the search | 10 | 5 | 5
Determine how to store a user's entire timeline in Firebase | 20 | 15 | 10
Spruce up the UI components of displaying posts | 15 | 5 | 5
Notice for when no "on this day" content or no posts in timeline | 5 | 0 | 0
Ensure account creation has valid email and password | 5 | 5 | 5
Adjust timestamps based on user-specified timezone | 10 | 5 | 2
Set up Map page | 40 | 30 | 15
Have Video playing functionality working | 10 | 10 | 10
Twitter and FB pagination | 20 | 10 | 5
Finish website and video | 10 | 10 | 10
Settings page updates |  |  | 5